## 2018
No. | Module | Task Name | Duration (days) | Start Date | End Date | Note | % Complete | Status | Assigned To
1 | Main Page | Add new cickable Icons, Outline facets of each category, Add main header & details background. | 9 | 2018-09-17 | 2018-09-25
2 | Landing Pages - Category | Add my prescription icon ,its division layout , enable dynamic counter of prescribed content.Add "Precribe" button layout into the contents. Functionality of precribe button. place the button to the new content division layout. Toggle hide/show for the contents division. | 15 | 2018-09-26 | 2018-10-10
3 | Leadership Competencies | Add Wheel Image into the right upper portion of the page for visual reference. This will serve as the navigation menu for each sub-category menu headers. Dynamically update no. of contents available for each menu header. Include back button to Main Page. | 14 | 2018-10-11 | 2018-10-24
4 | Leadership Competencies,Core Values,Customer Focus | Update content divisions to maximize the space of every sub category menu contents. New content layout that will fit the web parts . | 14 | 2018-10-25 | 2018-11-07
5 | Leadership Competencies,Core Values,Customer Focus | Toggle highlight of main category and sub-category menu header icons, Including no. of content availables per menu headers. | 14 | 2018-11-08 | 2018-11-21
7 | Prescription Page | add the page, icon, header & body table. Add checkboxes to select/deselect items,Remove item button & function. Dynamic function of fetching/showing of prescribed items into the table. Copy to clipboard functionality | 21 | 2018-11-22 | 2018-12-12
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23