## 2018
No. | Task Name | Duration (days) | Start Date | End Date | Note | % Complete | Status | Assigned To
1 | New Hire Foundation Training | 5 | 2018-05-21 | 2018-05-25
2 | New Hire Orientation ¦ PSTS Support Side by Side | 5 | 2018-05-28 | 2018-06-01
3 | Operation Support Team Side by Side ( Bryan & Deight) | 5 | 2018-06-04 | 2018-06-08
4 | Operation Support Team Side by Side ( 1 Day with Jared + Run Books Testing + Understand/Study Every PowerBi from Bryan Dashboards ) | 4 | 2018-06-11 | 2018-06-14
5 | Operation Support Team Side by Side (2 Days with Jared + Run Books Testing + Understand/Study Every PowerBi from Bryan,Jared Dashboards,Identified my role and future plans with the team ), Continues research | 5 | 2018-06-18 | 2018-06-22
6 | Updated to do list that came from Daniel Wolcoot, Powercoach, Roster and Sit In Updates. Started to Manually update some reports of Deight for the preparation of the week they will be out for trainings. Continues research | 5 | 2018-06-25 | 2018-06-29
7 | Research and Installation of Python. Mon-Tues Prepared Reports/ Tasks that was given to me for the 2days absence of Arj,bry and deight. Thurs & Fri BackUp Days. | 4 | 2018-07-02 | 2018-07-06
8 | Mon - Run BEO Reports, Installion of Selenium Bindings into python and automated testing of IMPower for deight. Updated other task from the action items that Dan was sent to me. On Going research. Run other reports of Arjee & Deight. | 5 | 2018-07-09 | 2018-07-13
9 | Updated the action items that dan sent me. | 5 | 2018-07-16 | 2018-07-20
10 | Updated schema of Powercoach - Main & Monitoring. | 5 | 2018-07-23 | 2018-07-27
11 | Updated schema of PSTS Users & Added Basic Authentication for the System. | 5 | 2018-07-30 | 2018-08-03
12 | Update System MockUp and UI | 5 | 2018-08-06 | 2018-08-10
13 | Update System Front End Functionalities using ReactJS and Updated the Medicine Cabinet | 5 | 2018-08-13 | 2018-08-17
14 | Update System Back End Functionalities (Powercoach Controller) using Lumen and Updated the Medicine Cabinet | 4 | 2018-08-20 | 2018-08-23
15 | Update Medicine Cabinet Phase 2 Scenarios, powercoach list and create functionalities for PSTS Web Tool. | 5 | 2018-08-27 | 2018-08-31
16 | Medicine Cabinet Project Timeline Estimation, Powercoach basic CRUD functionalities for main and monitoring | 4 | 2018-09-04 | 2018-09-07
17
18
19
20
21
22
23